## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 | [9 empty] | Plan Duration | Actual Start | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Risk Analysis | 2 | 2 | 2 | 2 | 100%
Class Diagram | 2 | 4 | 2 | 5 | 100%
Parser Class | 2 | 3 | 2 | 3 | 100%
Basic UI Plan | 2 | 2 | 2 | 2 | 100%
Game Pieces | 3 | 3 | 3 | 3 | 100%
Game Tiles | 3 | 3 | 3 | 3 | 100%
Test Documents | 4 | 7 | 4 | 7 | 10%
Software Documentation | 4 | 7 | 4 | 7 | 10%
Create UI Board | 4 | 3 | 4 | 4 | 100%
Create Menu Screens | 7 | 4 | 7 | 4 | 100%
Code Action Cards | 5 | 3 | 5 | 3 | 100%
Code Jail Tile | 3 | 3 | 3 | 3 | 100%
Code Turn System | 3 | 2 | 3 | 2 | 100%
Use Case Diagram | 5 | 2 | 5 | 3 | 100%
Code Money Transfer | 4 | 2 | 4 | 2 | 100%
Interaction with UI | 6 | 5 | 6 | 5 | 100%
Activity Diagrams | 7 | 2 | 7 | 2 | 100%
Sequence Diagram | 9 | 2 | 9 | 2 | 100%