## Sheet1
ID | Date Raised | Risk Description | Likelihood | Impact | Severity | Mitigating Action
1 | 2022-03-02 | Team members will not attend team meetings | 3 | 3 | 6 | Continue to message members and urge them to attend
2 | 2022-03-10 | Project will not be completed on time | 1 | 3 | 4 | Create a Gantt chart to schedule tasks to complete
3 | 2022-03-18 | Project brief is not fully understood | 2 | 2 | 4 | Read discussion forum for answers to questions
4 | 2022-03-24 | Tasks will not completed within schedule | 3 | 3 | 6 | Tasks can be split and given to other members to complete
5 | 2022-04-03 | Members will not be available over holiday | 3 | 3 | 6 | Increase work time after the holidays have ended
6 | 2022-04-05 | Covid-19 will affect work done | 3 | 2 | 5 | Plan ahead allowing time for absences
7 | 2022-04-14 | Data is lost and sets back progress | 2 | 3 | 5 | Create backups of all files and use cloud services